## KES Template
Region:
CNIC POC:
Installation:
Installation POC:
PHASE | TASKS | POC | Actual Date | NOTES
I 190 Days | Installation Requests Application Package | Installation
| CNIC Sends out Application Package | CNIC
| Installation completes application, CO Letter and passes to Region for review and sends to CNIC (1710.4) | Installation
| CNIC Evaluates the Application Package and responds to Installation (1710.4) | CNIC
| Installation Verifies Funding in writing for Project (1710.4) | Installation
| Package sent to Support contractor and/or Licensor w/CNIC assessment | CNIC
| Brand Support Contractor Reviews and/or Licensor Package/sends assessment to CNIC | Support Contractor
| Site Visit by CNIC HQ and/or Brand Support Contractor and/or Licensor | CNIC
| CNIC Go or No Go decision letter to Installation (1710.4) | CNIC
| CNIC sends Task Order to COR (HDQMWR-15-D-0005) | CNIC
| COR sends Assigned Task Order to Brand Support Contractor. | HQ Contracting
| Brand Support contractor sends Task Order to CNIC HQ to forward for signatures | Support Contractor
| Installation sends signed license agreement to region for signature then CNIC HQ for archiving | Installation
| Kick Off Call (KES), review 1710.4 instruction | ALL
II 160 Days | Installation Submits "as built" drawing and measurements to CNIC, if not supplied in Brand Application | Installation
| Installation submits before pictures of entire area effected by project to CNIC HQ | Installation
| Installation orders environmental testing | Installation
| Utilities/Hood use verification by Installation | Installation
| CNIC Reviews and edits installation drawing, sends to contractor for technical drawing draft, need list from Orion for building | CNIC
III 130 Days | CNIC Sends drawing # 1 revised to Contractor and Installation for call/discussion…need contact list | CNIC
| Contractor revises drawings #1 and distributes to the team for review | Support Contractor
| Call with Team to review drawings #1 | ALL
| Contractor revises previous drawing #2 and distributes to the team for review | Support Contractor
| Call with Team to review drawing #2 | ALL
| Contractor revises drawings to bring to Final stage | Support Contractor
| Call with Team to review final drawings | ALL
| Drawings go to Public Works for approvals, estimating cost, final CAD drawings | Installation |  | Events are concurrent with Public Works Time
| Final Menu is presented to installation | CNIC
| Installation obtains quotes for Small wares, Furniture & Equipment | Support Contractor
| Installation orders: FFE | Installation
| POS Selection/Order/with Install plan, architecture and reports needed | Installation
IV 110 Days | Construction begins-Count Down of Days to open | Installation |  | Events are concurrent with construction time
| Marketing Plan developed | Support Contractor
| Vendor Review (1710.4) | CNIC
| Construction Pictures at 25th day to HQ (1710.4) | Installation
| Food, Paper, Cleaning Supplies Order guide Developed | CNIC
| Staffing Guide developed, standard scheduler (1710.4) | Support Contractor
| Staff Headcount determined and agree upon by installation for target to be used for hiring. | Installation
| Construction Pictures at 45th day to HQ (1710.4) | Installation
| Training Plan Developed | Support Contractor
| SAP Accounts identified by IT for mapping POS | Installation
| Construction Pictures at 65th day to HQ (1710.4) | Installation
| SAP Nomenclature for Brand Name & Unit # | Installation
| Recruitment & Selection of employees (1710.4) | Installation
V 90 Days | Marketing Plan Begins-Pre Opening Advertising | Support Contractor
| Delivery of FFE | Support Contractor
| Contractor Pre Opening Meeting | Support Contractor
| First Food Order to Contractor and other vendors sent (sooner if OCONUS) | Installation
| POS install/programming | Installation
| Menu Screens & Feature Screens Install/programming | Installation
| Employee Orientation, to be completed before trainers arrive | Installation
| Installation submits after pictures of entire area effected by project to CNIC HQ | Installation
VI 30 Days | Construction Complete: Final punch list and hand over keys to operations | Installation
| If a Spinz location, hang trademark disclaimer sign | CNIC Trainer
| Final Sanitized Cleaning of operation | Installation
| Stocking of food for training | Installation
| Employee Training including Flash Report (1710.4) | Support Contractor
| Manager signs and recieves copy of 1710.4 | CNIC Trainer
| VIP Party to sample food...Marketing to Photgraph | Support Contractor
| Soft Opening to Public...Marketing to Photgraph | Support Contractor
VI | Post Opening Activity
| Week 1 Weekly call for progress | All
| Week 2 Weekly call for progress | All
| Week 3 Weekly call for progress | All
| Week 4 VCR | Support Contractor
| Week 5 Provide a complete schedule of pre-opening project costs to HQ (1710.4) | Installation
| Week 5 Weekly call for progress | All
| Week 6 Weekly call for progress | All
| Week 7 Weekly call for progress | All
| Week 8 VCR | Support Contractor
| Week 12 Monitoring and Reports | Support Contractor
| Week 13 Sales by item data submitted to HQ | Installation
| Week 15 Menu Engineering completed by Support Contractor | Support Contractor
| Week 16 Call to review & discuss Menu Eng. Results | CNIC
Note on B6: This is a qualifying package that has forms for completion. It will request information about the proposed space, base population, prior sales, etc.
Note on B7: Package is sent to the installation POC identified in the kick off call.
Note on B8: Package is sent to the N923D Program Manager; ray.nevin@navy.mil
Note on B9: CNIC HQ N923 Program Manager & team evaluates the package for feasibility
Note on B10: Region sends email confirmation of funds to CNIC HQ
Note on B11: CNIC HQ N923 sends package with comments to Contractor for evaluation.
Note on B12: Support contractor evaluates distribution feasibility and support.
Note on B13: Evaluate and become familiar with space, on base location, competition assessment
Note on B14: Program Manager will notify in writing to Regional POC
Note on B19: Purpose is to identify the team, layout roles & responsibilities, and establish a tentative time line.
Note on B20: Rough draft of space to be utilized and layout of traffic patterns
Note on B22: If applicable test proposed space for asbestos, or other abatement needs.
Note on B23: If Applicable verify that existing hood is inspected and in good operating order.
Note on B25: Details of production flow, space influence, equipment locations, power and plumbing, as well as storage.
Note on B26: Contractor takes input from the team and revises the drawings to capture the changes
Note on B27: All changes are reviewed for accuracy with team members and agree upon. Further changes are proposed and considered during the call for next draft at 90%.
Note on B28: Contractor takes input from the team and revises the drawings to capture the changes
Note on B29: All changes are reviewed for accuracy with team members and agree upon. Further changes are proposed and considered during the call for next draft at 100%.
Note on B30: Contractor takes input from the team and revises the drawings to capture the changes
Note on B31: All changes are reviewed for accuracy with team members and agree upon. Further changes are proposed and considered during the call for final acceptance by team.
Note on B32: Final 100% contractor drawings are given to PW for processing, bid to contractor
Note on B34: Contractor audits the drawings to the equipment list for accuracy and generates a quote to be sent to Region.
Note on B35: Region processes the purchase for small wares and equipment.
Note on B36: Region determines the POS system to be used and sources through Regional IT office or Millington It.
Note on B37: This varies by location and amount of work as well as any environmental abatement needs.
Note on B38: Contractor develops a yearly LTO calendar with recipes, nutritionals, cost cards.
Note on B39: Region identifies primary vendors for food purchases
Note on B41: Installation provides hours of operation, PDs, Rates of pay to Support Contractor. Support Contractor submits staffing guide to CNIC for reviewed, then sent to installation for review and call to discuss.
Note on B42: CNIC HQ drafts a line schedule and positions using the Region PD's.
Note on B43: The number of employees agreed upon are required to be on onboard before training is scheduled per the 1710.4
Note on B45: Contractor develops a n agenda for a Pre Opening Meeting (POM) and daily training for employees for menu and POS.
Note on B46: Regional IT works with Millington IT to map the SAP Accounts, provide a new manning convention in SAP, and ensure the activity (brand) is a stand alone cost center.
Note on B49: Region advertises positions and conducts interviews for new employee hires
Note on B50: Pre Opening Printed Material ships to Region for display in and around the new location to generate interest.
Note on B51: Equipment and Small wares arrive on site
Note on B52: Contractor conducts meeting with Region and CNIC HQ members on site to review training and last minute details.
Note on B53: Initial food order is placed for shipment to Region.
Note on B54: Designated POS is installed and menu loaded into program
Note on B55: Menu boards are installed and programmed with menu/specials
Note on B56: Employee training begins.
Note on B58: Final punch list completed and construction is finished
Note on B60: Employees and Contractor begin in unit with final sanitize and clean of operation
Note on B61: Employees stock food and learn prep to ready the brand for soft opening
Note on B62: Employee training finishes in preparation for soft opening
Note on B64: Employees serve food to small select group of Command invitees for trial and familiarization with menu and brand.
Note on B65: Base Command identifies in advance a ribbon cutting, PR, Grand Opening